## Gantt Chart
AgentShield — Gantt
Workstream / Objective | Oct 5–11 | Oct 12–18 | Oct 19–25 | Oct 26–Nov 1 | Nov 2–8 | Nov 9–15 | Objective / Outcome Reached
0 · Thinking & Planning | [6 empty] | M0 Architecture locked — Architecture, scope and implementation strategy locked
Threat model & scope | THINK + PLAN | [5 empty] | Trust boundaries, assumptions, non-goals, MVP scope
Architecture & interfaces | THINK + PLAN | [5 empty] | Core → policy → ledger → gateway → SDK → console → evaluation
1 · Foundations | [6 empty] | M1 Security kernel ready — Security kernel operational
Core lattice & provenance |  | CORE I | CORE II |  |  |  | Labels, join/meet, provenance DAG, tainted values, property tests
Capabilities & trifecta |  | CORE I | CORE II |  |  |  | Attenuation, delegation, TTL/epoch and lethal-trifecta invariant
2 · Enforcement | [6 empty] | M2 End-to-end enforcement — End-to-end deterministic enforcement
Cedar policy engine |  |  | POLICY | POLICY |  |  | Typed MCP schema, cached PDP, default-deny and fail-closed
Ledger & schema pinning |  |  |  | LEDGER | LEDGER |  | Hash chain, Merkle proofs, signed checkpoints, rug-pull detection
MCP gateway |  |  |  | GATEWAY | GATEWAY |  | M3 Human control operational — tools/list + tools/call interception and full decision pipeline
3 · Human Control | [6 empty] | Human approval and emergency revocation operational
Approval receipts |  |  |  |  | APPROVALS | APPROVALS | Ed25519 receipt, arg digest, nonce, expiry and reviewer tiers
Emergency revocation |  |  |  |  | REVOCATION | REVOCATION | M4 Defense stack integrated — Epoch invalidation, kill switch, pending cancellation, blast radius
4 · Depth | [6 empty] | Defense stack integrated
Dual-LLM quarantine |  |  |  |  | QUARANTINE | QUARANTINE | Symbolic var_ handles; raw untrusted content never reaches planner
Monotonic confinement | [5 empty] | CONFINEMENT | Subsumption checks; privilege expansions require human approval
Observability & shadow mode | [5 empty] | OBSERVABILITY | M5 Final security demonstration — OpenTelemetry, decision traces and log-only enforcement
5 · Surface & Proof | [6 empty] | Final security demonstration
Control-plane console | [5 empty] | CONSOLE | Policy editor, approval feed, audit explorer, replay and kill switch
Evaluation & adaptive attacks | [5 empty] | EVALUATION | AgentDojo, AgentDyn, adaptive attacks and pillar ablations

## Milestones & Objectives
Milestone | Target Date | Phase | Success / Objective Reached
M0 — Architecture locked | 11 Oct 2026 | Thinking & Planning | Threat model, scope, architecture, interfaces and delivery sequence approved.
M1 — Security kernel ready | 25 Oct 2026 | Foundations | Label lattice, provenance, Decision type, trifecta tracker and monotonic capabilities tested.
M2 — End-to-end enforcement | 1 Nov 2026 | Enforcement | Cedar PDP, ledger, schema pinning and MCP gateway can deterministically allow, deny and detect rug-pulls.
M3 — Human control operational | 8 Nov 2026 | Human Control | Cryptographic approvals, replay protection, expiry and emergency revocation are working.
M4 — Defense stack integrated | 15 Nov 2026 | Depth | Quarantine, monotonic confinement, SDK adapters and observability are integrated and tested.
M5 — Final security demonstration | 15 Nov 2026 | Surface & Proof | Console, benchmark evaluation, adaptive attacks, hardening and deployment documentation demonstrate the system.

## Weekly Objectives
Week | Dates | Primary Focus | Key Objectives | Milestone / Evidence
Week 1 | Oct 5–11 | Thinking & Planning | Threat model; trust boundaries; architecture; package interfaces; MVP scope; test strategy. | Architecture locked
Week 2 | Oct 12–18 | Foundations I | Workspace scaffold; CI; core lattice; provenance; Decision model; initial property tests. | Core primitives established
Week 3 | Oct 19–25 | Foundations II + Policy | Capabilities; attenuation; delegation; TTL/epoch; Cedar schema and PDP foundation. | Security kernel ready
Week 4 | Oct 26–Nov 1 | Enforcement | Hash/Merkle ledger; signed checkpoints; schema pinning; MCP gateway; full decision pipeline. | End-to-end enforcement
Week 5 | Nov 2–8 | Human Control + Depth | Approval receipts; Redis queue; revocation; kill switch; quarantine and SDK foundations. | Human control operational
Week 6 | Nov 9–15 | Depth + Surface & Proof | Monotonic confinement; observability; console; AgentDojo/AgentDyn; adaptive attacks; hardening; release docs. | Final security demonstration